## Slide 1: Project Planning

## Slide 2: How is it determined when Milestone 1.0 will be?
First working with customer to decide what features should be in Milestone 1.0
Based on features do rough estimation
Based on customer’s expected delivery date, go back to prioritize a workable feature set
Add more resource if needed
At here a milestone 1.0 release date is determined.

## Slide 3: What is the relationship between Milestones and Iterations?
A milestones usually is comprised of a couple of iterations.
Iteration is targeted with deliverable, iteration’s output will form milestone’s output
Iteration is based on team size, milestone is based on organization size. Big project could have different size team with different iterations
Iteration is user stories driven, milestone is features driven, before iteration, there should be a plan meeting work on what user stories iteration should work on. User stories is decided by features.

## Slide 4: How do you decide what a reasonable “baseline functionality” is
First working with customer to decide what features customer want
Prioritize all features with customer by importance
Make a project plan based on priority and dependencies
Put high priority features in before
Consider team capacity and velocity decide what should be put into baseline functionality

## Slide 5: What is the best basis for deciding how long each iteration will be?
Iteration should be short and balanced, ideally it’s between 2 weeks to 1 months
Consider the features you need deliver, break the features to unbreakable user stories
Consider biggest user stories’ estimation and team’s velocity, get a reasonable iteration time
In extreme situation, if there is a user stories is real big, also consider some unexpected risk, it’s reasonable in some situation, some user stories will be broken into two or more iterations

## Slide 6: How do “team size” and “velocity” figure into thinking about reasonable planning?
Ideally, consider the fixed time of iteration, the bigger team size, the more deliverable the team could possibly achieve.
Also velocity will improve deliverable as well
Use the following formula (Assume average N workday in one iteration) to get iteration capacity
  N * team size * velocity
Use the following formula to compute milestone capacity
  iteration capacity * iteration number